## CITY HALL DEPTS.
CITY HALL DEPTS.
Anticipated Capital Improvement projects for the next 5 - 10 years.
DEPARTMENT | LOCATION | DESCRIPTION | TOTAL ESTIMATED COST | START DATE (MONTH/YEAR) | ESTIMATED TIME TO COMPLETION | Form? | Manager Recommendation | Council Approved?
Planning/EconDev/PW | Downtown | VPI Construction - beginning 2027 | 600000 | 2027 | 2029 | Yes
Economic Development | Downtown Area | Public Restrooms/Visitor Center/Kiosk | TBD | FY2026 |  | Yes
Planning/EconDev/PW | High Street/Myrick | Thriving Communities Partnership | TBD | Started | 2029 | Yes
PW/EconDev/Manager | Franklin St. Parklet | Closing lower Franklin Street to create a permanent park - Planning, Design & Engineering Phase | 30,000+ |  |  | Yes
PW/IT/EconDev/Manager | Downtown Area | City owned Light Pole Replacement | 2000000 | TBD - see description form. |  | Yes
Plannin/Econ Dev/PW | Downtown Area | Multiuse PATH | 2500000 | 2026 | 2029 | Yes
EconDev/Facilities | URCI | URCI upgrades | 70000 | 2025 | 2027 | Yes
IT/Communications/Manager | Digital infrstructure | Website Upgrade/Branding Initiative | 105000 | FY2025 | FY2026
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Updating the website aesthetic in the upcoming Fiscal Year via current provider for about ~$10,000

## FACILITIES
FACILITIES
Anticipated Capital Improvement projects for the next 5 - 10 years.
LOCATION | DESCRIPTION | TOTAL ESTIMATED COST | START DATE (MONTH/YEAR) | Manager Recommendation | Council Approval
City Hall | Interior Remodeling | 330000 | FY25 | Yes
City Hall | Lower City Hall Parking Lot Repavement | 201250 | FY26 | No
City Hall | Cupola | 200000 | FY26
City Hall | Wood trim painting/replacement | 50000? | FY26
City Hall | Repoint & replace/repair bricks on entire building | 250000 | FY26
City Hall | Front steps complete renovation | 250000 | FY26
| Radio Tower repairs | 30000 | FY26
City Hall | Reseal auditoirium and planning windows; repair sheetrock ceilings in City Manager hallway and accross from IT | FEMA request
Note on A5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Amanda Ray @Michael Harris are you getting a quote for the CH pavement? Reply: Adam was wroking with Northeast paving to get quotes but they only gave us a quote for the other two paving projects...I will email Greg Dexter to follow up! Reply: thank you!

## FIRE
FIRE DEPT.
Anticipated Capital Improvement projects for the next 5 - 10 years.
LOCATION | DESCRIPTION | TOTAL ESTIMATED COST | START DATE (MONTH/YEAR) | ESTIMATED TIME TO COMPLETION | PRIORITY (LOW/MED./HIGH) | Manager Recommendation | Council Approval
Fire Department | Repalce Engine 2 (2016) | 1000000 | 2025 | 2026 | High
Fire Department | Reaplce Tanker 4 (1998) | 600000 | 2025 | 2027
Fire Department | Command staff vehicles ( 3) | 250000 | 2025 | 2027
Fire Department | Purchase second ambulance | 600000 | 2026 | 2028
Fire Department | remodeling living quarters to accomidate 7-8 firefghters | Need Quote | 2026 | 2027
Fire Department | Replace Engine 7 (2007) | 1000000 | 2027 | 2029
Fire Department | Repalce ladder 1 (2010) | 2000000 | 2027 | 2030
Fire Department | Build North Ellsworth Station | Need Quote | 2027 | 2030
Fire Departtment | Bullet proof vests | 17000 | 2027 | 2028
Fire Department | Remount Ambulance (2020) -Reuse Chassis for service or BC Truck | 400000 | 2028 | 2029
Fire Department | Replace Portable Radios | 90000 | 2028 | 2030
Fire Department | Replace mobile radios all fire apparatus | 40000 | 2028 | 2030
Fire Department | Replace Truck 3 (2015) with a traditionl mini-pumper style Brushtruck | 500000 | 2029 | 2030

## LIBRARY
LIBRARY DEPT.
Anticipated Capital Improvement projects for the next 5 - 10 years.
LOCATION | TYPE OF PURCHASE | DESCRIPTION | TOTAL ESTIMATED COST | START DATE (MONTH/YEAR) | Manager Recommendation | Council Approval
LIBRARY DEPT. |  | HVAC Improvements | 250000 | FY 25
LIBRARY DEPT. |  | Sprinkler System Installation | 56500 | FY 25
LIBRARY DEPT. |  | Match For CDS | ?

## HIGHWAY
HIGHWAY
Anticipated Capital Improvement projects for the next 5 - 10 years. (LOCAL ROADS IN SEPARATE SHEET)
Department | Division | Type of Purchase | DESCRIPTION | TOTAL ESTIMATED COST | START DATE (MONTH/YEAR) | ESTIMATED TIME TO COMPLETION | PRIORITY (LOW/MED./HIGH) | Manager Recommendation | Council Approved?
Public Works | Highway | Equipment | PLOW TRUCK | 300000 | 2024-10-01 | 2025-10-01 | Medium
Public Works | Harbor | Grant Match | DREDGING | 500000
Public Works | Harbor |  | Harbor Park Parking Lot Paving- Pave 2" 12.5MM over existing | 90750
Public Works | Harbor |  | Harbor Park Parking Lot Paving- Pave 2" 12.5MM over Gravel Section | 38280
Public Works | Harbor |  | Engineering for Commercial Dock | 150000
Excavator
Harbor upgrades
Staff Locker Room

## POLICE
POLICE DEPT.
Anticipated Capital Improvement projects for the next 5 - 10 years.
LOCATION | TYPE OF PURCHASE | DESCRIPTION | TOTAL ESTIMATED COST | START DATE (MONTH/YEAR) | ESTIMATED TIME TO COMPLETION | PRIORITY (LOW/MED./HIGH) | Manager Recommendation | Council Approved?
POLICE DEPT. |  | Evidence room collapasble storage for weapons | 25000 | FY26 | FY26
POLICE DEPT. |  | Fingerprint scanner | 6800 | FY26 | FY26
POLICE DEPT. |  | Drone's & Software- Reconstructions (currenlty 2 drones - may be grant fund) | 15000 | FY27 | FY27
POLICE DEPT. |  | Rifles w/ site (purchased in 2018) will have trade to take price down | 33000 | FY29 | FY29
POLICE DEPT. |  | Handguns (purchased in 2019) will have trade to take price down | 12150 | FY29 | FY29
POLICE DEPT. |  | K-9 - replace current | 15000 | FY29 | FY29
POLICE DEPT. |  | Portable Radios (currently 20) 10 years old in 2030-no warranty after 5 yrs | 52000 | FY30 | FY30
POLICE DEPT. |  | Body & Cruier Cameras - Motorola Soulutions - purchased FY25 | 300,000 over 5 years | FY30 | FY35
POLICE DEPT. |  | Tasers - purchased FY25 | 150,000 over 5 years | FY30 | FY35
POLICE DEPT. |  | Cruiser Radios (currenlty 18) 10 years old in 2032-no warranty after 5 yrs | 45000 | FY32 | FY32
POLICE DEPT. |  | Avtect Dispatch Consoles - All emergency servies - Replace 2 consoles | 14000 | FY30 (1) &FY33 (1)
POLICE DEPT. |  | Avtect Dispatch Consoles - All emergency servies - Add 3rd console | 26000 | FY27
POLICE DEPT. |  | Repeater replacements (4 site) Polce & Fire (purchased in 2020) - no warranty after 5 years | 46000 | FY30 - FY35 | FY30 - FY35
POLICE DEPT. |  | Paving | 125000 | FY25
POLICE DEPT. |  | Sign out front | 15000 | FY25

## School Dept.
School Dept.
Anticipated Capital Improvement projects for the next 5 - 10 years.
LOCATION | TYPE OF PURCHASE | DESCRIPTION | TOTAL ESTIMATED COST | START DATE (MONTH/YEAR) | ESTIMATED TIME TO COMPLETION | PRIORITY (LOW/MED./HIGH) | Manager Recommendation | Council Approved?
Track and Field |  | Need re-do the track and light poles at this facility as well as the soccer field | 1.6 million as a high, high estimate of all phases of the project | would like to get bids this winter with project completion by mid August 2025 | 4-7 months | High

## WATER
WATER DEPT.
Anticipated Capital Improvement projects for the next 5 - 10 years.
LOCATION | TYPE OF PURCHASE | DESCRIPTION | TOTAL ESTIMATED COST | START DATE (MONTH/YEAR) | ESTIMATED TIME TO COMPLETION | PRIORITY (LOW/MED./HIGH) | Manager Recommendation | Council Approved?
Surry Rd. |  | Add Contingency for the Surry Rd Water Main Project | 150000 | FY 25
Myrick St./DEH Loop |  | Connect Myrick St. to DEH | ? | after fy25
Upper Church St./Oak St. |  | Connect upper Church St. to Oak St. | ? | after fy25
Park St. |  | Eliminate two dead ends. | ? | after fy25
Parcher St./Birch Ave. |  | Connect Birch and Parcher. | ? | after fy25
Christian Ridge Rd. |  | Redundency Main. Bucksport Rd. To Bangor Rd. | ? | after fy25
DEH to High St. |  | Connect DEH to High St. directly | ? | after fy25
Bucksport Rd. |  | Redundency Transmission Main | ? | after fy25
Water Tank |  | Tank on top of Beckwith Hill | ? | after fy25
Bar Harbor Rd. |  | Extend main to Trenton Town Line | ? | after fy25
Beals Ave. |  | Renew water main | ? | after fy25
Union St. |  | Eliminate two dead ends. | ? | after fy25
Oak St. |  | Renew Water main | ? | after fy25
Mid. And Lower Church St. |  | Renew and extend main from Oak to State St. | ? | after fy25
State St. |  | Increase main from 8" to 12" | ? | after fy25

## WASTEWATER
WASTEWATER DEPT.
Anticipated Capital Improvement projects for the next 5 - 10 years.
LOCATION | TYPE OF PURCHASE | DESCRIPTION | TOTAL ESTIMATED COST | START DATE (MONTH/YEAR) | ESTIMATED TIME TO COMPLETION | PRIORITY (LOW/MED./HIGH) | Manager Recommendation | Council Approved?
WASTEWATER DEPT. |  | Upgrade the Dewatering process | 3000000 | 2025-10-25 | 6 months | high
Upgrade the South St Siphon

## Other Capital Projects
OTHER CAPITAL PROJECTS
Anticipated Capital Improvement projects for the next 5 - 10 years. (LOCAL ROADS IN SEPARATE SHEET)
Department | DESCRIPTION | TOTAL ESTIMATED COST | START DATE (MONTH/YEAR) | Manager Recommendation | Council Approval
Store St Retaining Wall
EV Fleet
Pumpstation Point
Dam improvements
Knowlton Park
River Walk
Public Art
Main Street/High Street Beautification

## ROADS
City of Ellsworth Work Plan: Local Roads
In order of recommendation BY YEAR |  |  |  | BOND | START YEAR
Foster Street | Mill and Fill 2" on Foster St.: 24' x 2157, 656 Tons one lift of 12.5M. |  |  | 87904 | 2024
Elm Street | Surface Elm Street: 22' X 910’; 184 Tons @ 1.5" (MILL 1.5"). |  |  | 24656 | 2025
Happytown Road | Shim Happytown: 23' X 4300', 302 Tons @ 1/2"; $42,280. Surface Happytown: 23' X 4300', 604 Tons @ 1"; $80,936. |  |  | 123216 | 2025
Grant Street (Upper) | Approximate 21'x 3300' reclaim, grade, pave 2" 12.5mm binder and 1.25" of 12.5mm surface. |  |  | 195750 | 2025
Grant Street (Lower) | Approximate 20'x 1700' reclaim, grade, pave 2" 12.5mm binder and 1.25" of 12.5mm surface. |  |  | 105000 | 2025
|  | This section needs three culverts and an F-type basin. This was on the 2024/2025 list. |  |  | 2025
Western Ave./Holt/Argon | Shim: 16' X 2200', 107 Tons @ 1/2"; $14,980. Surface: 16' X 2200', 214 Tons @ 1"; $28,890. |  |  | 43870 | 2025
Hancock Street | Shim Hancock Street: 19' X 900', 53 Tons @ 1/2"; $7,420. Surface Hancock Street: 19' X 900', 105 Tons @ 1"; $14,070. |  |  | 21490 | 2025
|  | This is NOT ready. An F-type basin and 240 feet of drainage pipe are needed. |  |  | 2025
Red Bridge Road | Shim Red Bridge Section 1: 22' X 2700', 273 Tons @ 3/4"; $38,220. Surface Red Bridge Section 1: 22' X 2700', 363 Tons @ 1"; $48,642. |  |  |  | 2025
| Shim Red Bridge Section 2: 21' X 2400', 154 Tons @ 1/2"; $21,560. Surface Red Bridge Section 2: 21' X 2400', 318 Tons @ 1"; $42,930. |  | Total for both sections: | 111352 | 2025
Birch Street | Shim Birch Street: 23' X 1100', 78 Tons @ 1/2"; $10,920. Surface Birch Street: 23' 1100', 160 Tons @ 1"; $21,440. Concrete curbing $6000. |  |  | 38360 | 2025
Maddocks Ave. | Shim Maddocks Street: 21'X1500', 145 Tons @3/4"; $20,300. Surface Maddocks Street: 21'X1500', 200 Tons @1"; $26,800. |  |  | 47100 | 2025
|  | This is NOT ready. EPW has three cross pipes and ditching to be done, along with gravel added. |  |  | 2025
Boggybrook Road | Reclaim and pave 3". 23' X 2850', 1250 TONS 2 LIFTS OF 12.5MM. GRADING BY OTHERS. |  |  | 167500 | 2025
Bayview | 19' X 1075', 62 Tons @ 1/2"; $8,680. 19' X 1075', 124 Tons @ 1"; $16,740. |  |  | 25420 | 2025
Indsutrial | Pave 3". 24' X 350', 160 TONS. 2 LIFTS OF 12.5MM. |  |  | 21440 | 2025
Handwork butt joints | Driveway entrances |  |  | 35000 | 2025
Milling |  |  |  | 56875 | 2025
Mobilization |  |  |  | 20000 | 2025
Happytown/Winkumpaugh | Approximately 22' x3200'. City to grade existing gravel. Pave 2" of 12.5mm base and 1.25" of 12.5mm surface. The 1.25" surface lift only will continue up Winkumpaugh Road to the end of pavement. |  |  | 184375 | 2025
Gary Moore Rd. | Reclaim and binder 2" of 12.5MM |  |  | 282000 | 2025
Gary Moore Rd. | Surface 1" 9.5MM |  |  | 136000 | 2025
1727308

## Settings (hidden)
Settings
CALCULATED VALUES DO NOT EDIT
FY Start Date | 2024-07-01 | Calculated Fiscal Year | 2025
|  | Calculated Prior Year 1 | 2023-07-01
|  | Calculated Prior Year 2 | 2022-07-01
|  | Calculated End of FY Date | 2025-06-30
|  | Calculated End of FY Date Prior Yr 1 | 2024-06-30
|  | Calculated End of FY Date Prior Yr 2 | 2023-06-30
|  | Calculated End of FY Date Prior Yr 3 | 2022-06-30